## Sheet1
Change Request Id | Data submitted | Submitted by | Description of Change | Resaon/Justification | Impact/Analysis | Priority | Approval Status | Approved by & Date
1 | 2026-06-12 | Exam Controller | online exam registrartion module for students | reduce paper work, reduce queues, donot visit university as a inperson for registration | Core module, need database, login/signup UI ,Exam registration form UI | High | Approved | Project Manager, 13-Jun-26
2 | 2026-06-11 | Project Manager | Need Admin dashboard, generate report for student grade, download/export Excel format | Admin/Exam Controller needs reports without IT help | Admin Dashboard, export/download business logic | Medium | Approved | Project Manager, 13-Jun-26
3 | 2026-06-10 | Student Affair | Auto-generate and email roll number slips as PDF | Students waste days waiting in lines to collect slips | PDF library needed, Email server config required | Medium | Approved | Project Manager, 13-Jun-26
4 | 2026-06-13 | Fiance Dept | Add penalty fee auto-calculation for late registration | Manual penalty calculation causes errors and disputes | Small logic change in payment module | Low | Pending | Under Review